## built Bug report
BUG ID | SECTION | BUG CATEGORY | BUG TITLE | ENVIRONMENT DETAILS | BUG DESCRIPTION | SEVERITY | PRIORITY | REPORTED BY | DATE | STEPS TO REPRODUCE | TEST DATA (OPTIONAL) | ACTUAL RESULT | EXPECTED RESULT | SCREENSHORT/VIDEO CLIP | Suggestion for Improvement/Additional Note | BUG STATUS | TESTER COMMENT | DEV ASSIGNED | DEV COMMENT
BG_001 | Empty Cart – Discount Summary | Product Defect | Discount value displays as "-$0.00" after cart is emptied following an invalid discount code | Application: Shopping Cart UI Browser: Microsoft Edge Automation: Playwright (product_quantity.spec.ts) Project: edge | After applying an invalid discount code and removing all items from the cart, the Discount field displays "-$0.00" instead of "$0.00". This indicates the UI is retaining a negative sign for a zero discount amount even though no discount is applied and the cart is empty. | Normal (Medium) | Medium | Raxit Sharma | 2026-07-18 | 1. Launch the application. 2. Add 5 products to the cart. 3. Open the cart. 4. Enter invalid discount code 0000 and click Apply. 5. Verify the "Invalid code." message appears. 6. Remove all products from the cart. 7. Observe the Discount field in the cart summary. | Discount Code: 0000 | Cart displays "Your cart is empty." but the Discount field shows "Discount: -$0.00". The automated validation fails because the displayed text is incorrect. | When no valid discount is applied and the cart is empty, the Discount field should display "Discount: $0.00" (without the negative sign). | bug_1.png |  | New
BG_002 | Checkout – Email Validation | Product Defect | Checkout accepts invalid email address and places the order | Application: Shopping Cart UIBrowser: Microsoft EdgeAutomation: Playwright (product_checkout.spec.ts)Project: edge | The checkout form does not properly validate the email address. An invalid email format is accepted, allowing the user to successfully place an order. This bypasses input validation and results in an order being created with an invalid email address. | High (Critical Functional Defect) | High | Raxit Sharma | 2026-07-18 | 1. Launch the application.2. Add products to the cart.3. Open the cart.4. Apply discount code SAVE10 (optional).5. Proceed to Checkout.6. Enter valid customer details but provide an invalid email address (e.g., missing @ or missing domain).7. Click Place Order.8. Observe the checkout result. | Customer: Emily DavisInvalid Email Examples: [link removed], emily@, [link removed] | The application accepts the invalid email address and successfully places the order without displaying a validation error. | The application should validate the email format, prevent the order from being submitted, and display an appropriate validation message until a valid email address is entered. | bug_2.png |  | New
BG_003 | Cart – Order Total Calculation | Product Defect | Grand total is displayed with incorrect decimal precision | Application: Shopping Cart UI Browser: Microsoft Edge Automation: Playwright Project: edge | The cart grand total is displayed with more than two decimal places, resulting in an improperly formatted currency value. Currency amounts should always be rounded and displayed to exactly two decimal places. | Normal (Medium) | Medium | Raxit Sharma | 2026-07-18 | 1. Launch the application. 2. Add the required products to the cart. 3. Perform the actions that calculate the cart total. 4. Navigate to the cart summary. 5. Observe the Grand Total value. | Expected Total: $691.64 | The Grand Total is displayed as Total: $697.2916, showing four decimal places instead of a properly formatted currency value. | The Grand Total should be displayed as a valid currency amount with exactly two decimal places (e.g., Total: $697.29 or the correctly calculated total if the expected amount is $691.64). | bug_3.png |  | New
BG_004 | Cart – Tax Calculation | Product Defect | Tax amount is calculated/displayed incorrectly and uses more than two decimal places | Application: Shopping Cart UI Browser: Microsoft Edge Automation: Playwright Project: edge | The tax value displayed in the cart summary is incorrect. Instead of calculating 8% tax correctly and formatting it as a currency value with two decimal places, the application displays an incorrect amount with four decimal places. | Normal (Medium) | High | Raxit Sharma | 2026-07-18 | 1. Launch the application. 2. Add the required products to the cart. 3. Proceed to the cart summary where tax is calculated. 4. Observe the Tax (8%) value. | Expected Tax: $22.07 | The application displays Tax (8%): $56.5136, which is both an incorrect tax amount and an improperly formatted currency value (four decimal places). | The application should correctly calculate the 8% tax and display it as Tax (8%): $22.07 (or the correct calculated value), formatted with exactly two decimal places. | bug_4.png |  | New
BG_005 | Cart – Order Summary | Product Defect | Incorrect subtotal displayed in cart summary | Application: Shopping Cart UIBrowser: Microsoft EdgeAutomation: PlaywrightProject: edge | The cart summary displays an incorrect subtotal after products are added to the cart. The calculated subtotal does not match the expected value based on the selected products, indicating an issue in the subtotal calculation or pricing logic. | Normal (Medium) | High | Raxit Sharma | 2026-07-18 | 1. Launch the application.2. Add the required products to the cart.3. Open the cart and navigate to the order summary.4. Observe the Subtotal value. | Expected Subtotal: $306.47 | The application displays Subtotal: $706.42, which does not match the expected subtotal. | The application should correctly calculate and display the subtotal as Subtotal: $306.47 (or the correct value based on the selected products). | bug 5.png |  | New
BG_006 | Cart – Discount Calculation | Product Defect | Discount amount is calculated incorrectly in the order summary | Application: Shopping Cart UI Browser: Microsoft Edge Automation: Playwright Project: edge | The discount displayed in the order summary is incorrect after applying the discount code. The calculated discount does not match the expected value based on the subtotal, indicating an issue in the discount calculation logic. | Normal (Medium) | High | Raxit Sharma | 2026-07-18 | 1. Launch the application. 2. Add the required products to the cart. 3. Apply a valid discount code. 4. Open the order summary. 5. Observe the Discount value. | Expected Discount: -$30.65 | The application displays Discount: -$70.64, which is significantly higher than the expected discount amount. | The application should correctly calculate and display the discount as Discount: -$30.65 (or the correct value based on the applied discount and subtotal). | bug 6.png |  | New
BG_007 | Cart – Inventory Validation | Product Defect | Out-of-stock product can be added to the cart | Application: Shopping Cart UIBrowser: Microsoft EdgeAutomation: PlaywrightTest File: verifyProject: edge | An item marked as out of stock can still be added to the shopping cart. The cart shows a quantity of 1 instead of preventing the addition, indicating that stock availability is not being validated before adding the product. | High | High | Raxit Sharma | 2026-07-18 | 1. Launch the application.2. Identify a product marked as Out of Stock.3. Click Add to Cart for the out-of-stock product.4. Open the shopping cart.5. Verify the product quantity in the cart. | Out-of-stock product | The out-of-stock product is successfully added to the cart with a quantity of 1. | The application should prevent out-of-stock products from being added to the cart. The quantity should remain 0, or the Add to Cart action should be disabled with an appropriate message (e.g., "Out of Stock"). | bug 7.png |  | New
BG_008 | Homepage – Cart Counter | Product Defect | Cart badge/count is not updated after adding products to the cart | Application: Shopping Cart UIBrowser: Microsoft EdgeAutomation: PlaywrightProject: edge | After adding five products to the cart from the homepage, the cart counter does not update to display Cart (5). The expected cart badge cannot be found, indicating that the cart count is not being refreshed or displayed correctly. | Normal (Medium) | High | Raxit Sharma | 2026-07-18 | 1. Launch the application.2. Verify the homepage is loaded.3. Click Add to Cart for five different products.4. Observe the cart badge/count displayed on the homepage. | Add any five available products. | The Cart (5) badge is not displayed. The element cannot be found, causing the validation to fail. | After adding five products, the cart badge should update immediately and display Cart (5), accurately reflecting the number of items in the cart. | bug 8.png |  | New

## test cases
StoreFront Application Test Tracker
TC ID | Module | Test Scenario | Expected Result | Status
TC-001 | Module 1 – Application Launch | Verify launch web application | Home page loads successfully | Passed
TC-002 | Module 1 – Application Launch | Verify page title Shop | Correct page title displayed | Passed
TC-004 | Module 1 – Application Launch | Verify default cart count | Cart displays (0) | Failed
TC-005 | Module 1 – Application Launch | Verify refresh application | Application reloads without errors | Passed
TC-006 | Module 2 – Product Listing | Verify all products displayed | All 5 products visible | Passed
TC-007 | Module 2 – Product Listing | Verify product name | Correct product names displayed | Passed
TC-008 | Module 2 – Product Listing | Verify product prices | Prices match specification | Passed
TC-009 | Module 2 – Product Listing | Verify inventory count | Inventory displayed correctly | Passed
TC-010 | Module 2 – Product Listing | Verify Add to Cart button | Button available for every product | Passed
TC-011 | Module 2 – Product Listing | Verify product cards alignment | Cards aligned properly | Passed
TC-012 | Module 2 – Product Listing | Verify duplicate products | No duplicate products | Passed
TC-013 | Module 2 – Product Listing | Verify product ordering | Products appear in expected order | Passed
TC-014 | Module 3 – Product Inventory | Verify Product with stock >0 | Add button enabled | Failed
TC-015 | Module 3 – Product Inventory | Verify Product with stock =0 | Cannot add to cart | Failed
TC-016 | Module 3 – Product Inventory | Verify stock label updates | Stock decreases after add | Passed
TC-017 | Module 3 – Product Inventory | Verify Add last available item | Inventory becomes zero | Passed
TC-018 | Module 3 – Product Inventory | Verify Attempt exceeding stock | Not allowed | Passed
TC-019 | Module 3 – Product Inventory | Verify Refresh page after stock update | Stock persists if expected | Passed
TC-020 | Module 3 – Product Inventory | Verify inventory never negative | Stock never below zero | Passed
TC-021 | Module 4 – Add to Cart | Verify Add first item | Item added | Passed
TC-022 | Module 4 – Add to Cart | Verify Add multiple different items | All appear in cart | Passed
TC-023 | Module 4 – Add to Cart | Verify Add same product twice | Quantity increases | Passed
TC-024 | Module 4 – Add to Cart | Verify Add every product | All items added | Passed
TC-025 | Module 4 – Add to Cart | Verify Add unavailable item | Cannot add | Failed
TC-026 | Module 4 – Add to Cart | Verify Rapid multiple clicks | Quantity never exceeds inventory | Passed
TC-027 | Module 4 – Add to Cart | Verify Cart opens correctly | Added items visible | Passed
TC-028 | Module 4 – Add to Cart | Verify item subtotal | Correct calculation | Passed
TC-029 | Module 5 – Cart Indicator | Verify Empty cart | Cart(0) | Failed
TC-030 | Module 5 – Cart Indicator | Verify Add one item | Cart(1) | Failed
TC-031 | Module 5 – Cart Indicator | Verify Add multiple quantities | Count equals total quantity | Passed
TC-032 | Module 5 – Cart Indicator | Verify Remove one item | Count decreases | Passed
TC-033 | Module 5 – Cart Indicator | Verify Remove all items | Cart(0) | Passed
TC-034 | Module 5 – Cart Indicator | Verify Refresh cart page | Count remains accurate | Passed
TC-035 | Module 6 – Cart Page | Verify Open cart | Cart page loads | Passed
TC-036 | Module 6 – Cart Page | Verify Empty cart view | Empty state shown | Passed
TC-037 | Module 6 – Cart Page | Verify product rows | Products listed correctly | Passed
TC-038 | Module 6 – Cart Page | Verify quantity controls | + and - visible | Passed
TC-039 | Module 6 – Cart Page | Verify Remove button | Remove visible | Passed
TC-040 | Module 6 – Cart Page | Verify subtotal display | Correct subtotal | Passed
TC-041 | Module 7 – Quantity Update | Verify Increase quantity | Quantity increases | Passed
TC-042 | Module 7 – Quantity Update | Verify Decrease quantity | Quantity decreases | Passed
TC-043 | Module 7 – Quantity Update | Verify Quantity reaches zero | Item removed or zero handled | Passed
TC-044 | Module 7 – Quantity Update | Verify Increase beyond inventory | Not allowed | Passed
TC-045 | Module 7 – Quantity Update | Verify Rapid increment | Inventory respected | Passed
TC-046 | Module 7 – Quantity Update | Verify Rapid decrement | No negative quantity | Passed
TC-047 | Module 7 – Quantity Update | Verify Update multiple items | Totals update correctly | Passed
TC-048 | Module 7 – Quantity Update | Verify subtotal after update | Correct calculation | Passed
TC-049 | Module 8 – Remove Item | Verify Remove one item | Item removed | Passed
TC-050 | Module 8 – Remove Item | Verify Remove last item | Cart empty | Passed
TC-051 | Module 8 – Remove Item | Verify Remove middle item | Remaining items unchanged | Passed
TC-052 | Module 8 – Remove Item | Verify Remove repeatedly | No errors | Passed
TC-053 | Module 8 – Remove Item | Verify Remove updates total | Total recalculated | Passed
TC-054 | Module 9 – Discount Code | Verify Apply SAVE10 | 10% discount applied | Passed
TC-055 | Module 9 – Discount Code | Verify Discount recalculates subtotal | Correct | Passed
TC-056 | Module 9 – Discount Code | Verify Total updated | Correct | Passed
TC-057 | Module 9 – Discount Code | Verify Tax recalculated | Correct | Passed
TC-058 | Module 9 – Discount Code | Verify Shipping unchanged | 5 | Passed
TC-059 | Module 9 – Discount Code | Verify Invalid code | Error displayed | Passed
TC-060 | Module 9 – Discount Code | Verify Empty code | Validation shown | Passed
TC-061 | Module 9 – Discount Code | Verify Spaces only | Invalid | Passed
TC-062 | Module 9 – Discount Code | Verify Lowercase save10 | Case behavior verified | Passed
TC-063 | Module 9 – Discount Code | Verify Mixed case | Correct handling | Passed
TC-064 | Module 9 – Discount Code | Verify Special characters | Invalid | Passed
TC-065 | Module 9 – Discount Code | Verify SQL injection string | Safe rejection | Passed
TC-066 | Module 9 – Discount Code | Verify HTML input | Escaped safely | Passed
TC-067 | Module 9 – Discount Code | Verify Apply twice | No stacking | Passed
TC-068 | Module 9 – Discount Code | Verify Multiple discount attempts | Only one valid discount | Passed
TC-069 | Module 10 – Price Calculation | Verify Single product subtotal | Correct | Passed
TC-070 | Module 10 – Price Calculation | Verify Multiple products subtotal | Correct | Passed
TC-071 | Module 10 – Price Calculation | Verify Large quantities | Correct | Passed
TC-072 | Module 10 – Price Calculation | Verify Decimal calculations | Accurate | Passed
TC-073 | Module 10 – Price Calculation | Verify Discount applied | Correct | Passed
TC-074 | Module 10 – Price Calculation | Verify Tax applied | 8% | Passed
TC-075 | Module 10 – Price Calculation | Verify Shipping added | 5 | Passed
TC-076 | Module 10 – Price Calculation | Verify Final total | Formula correct | Failed
TC-077 | Module 10 – Price Calculation | Verify Total updates after remove | Correct | Failed
TC-078 | Module 10 – Price Calculation | Verify Total updates after quantity change | Correct | Failed
TC-079 | Module 11 – Tax | Verify tax rate | 8% | Passed
TC-080 | Module 11 – Tax | Verify Tax after discount | Correct | Failed
TC-081 | Module 11 – Tax | Verify Tax with one item | Correct | Failed
TC-082 | Module 11 – Tax | Verify Tax with many items | Correct | Failed
TC-083 | Module 11 – Tax | Verify Decimal rounding | Correct | Failed
TC-084 | Module 12 – Shipping | Verify Fixed shipping | 5 | Failed
TC-085 | Module 12 – Shipping | Verify Shipping with discount | Still $5 | Passed
TC-086 | Module 12 – Shipping | Verify Shipping after remove | Still $5 | Passed
TC-087 | Module 12 – Shipping | Verify Shipping empty cart | Business rule verified | Passed
TC-088 | Module 13 – Checkout Page | Verify Checkout page loads | Success | Passed
TC-089 | Module 13 – Checkout Page | Verify Full Name field visible | Yes | Passed
TC-090 | Module 13 – Checkout Page | Verify Email field visible | Yes | Passed
TC-091 | Module 13 – Checkout Page | Verify Gift message visible | Yes | Passed
TC-092 | Module 13 – Checkout Page | Verify Place Order button | Visible | Passed
TC-093 | Module 14 – Checkout Validation | Verify Empty name | Validation | Passed
TC-094 | Module 14 – Checkout Validation | Verify Spaces only | Validation | Passed
TC-095 | Module 14 – Checkout Validation | Verify Valid name | Accepted | Passed
TC-096 | Module 14 – Checkout Validation | Verify Long name | Accepted | Passed
TC-097 | Module 14 – Checkout Validation | Verify Numeric name | Validation if required | Passed
TC-098 | Module 14 – Checkout Validation | Verify Special characters | Expected behavior | Passed
TC-099 | Module 14 – Checkout Validation | Verify Empty email | Validation | Passed
TC-100 | Module 14 – Checkout Validation | Verify Valid email | Accepted | Passed
TC-101 | Module 14 – Checkout Validation | Verify Missing @ | Invalid | Failed
TC-102 | Module 14 – Checkout Validation | Verify Missing domain | Invalid | Passed
TC-103 | Module 14 – Checkout Validation | Verify Invalid format | Invalid | Passed
TC-104 | Module 14 – Checkout Validation | Verify Uppercase email | Accepted | Passed
TC-105 | Module 14 – Checkout Validation | Verify Leading spaces | Trimmed | Passed
TC-106 | Module 14 – Checkout Validation | Verify Trailing spaces | Trimmed | Passed
TC-107 | Module 14 – Checkout Validation | Verify Empty message | Allowed | Passed
TC-108 | Module 14 – Checkout Validation | Verify Normal text | Saved | Passed
TC-109 | Module 14 – Checkout Validation | Verify Long message | Handled | Passed
TC-110 | Module 14 – Checkout Validation | Verify Emoji | Accepted | Passed
TC-111 | Module 14 – Checkout Validation | Verify HTML | Escaped | Passed
TC-112 | Module 14 – Checkout Validation | Verify SQL injection | Safe | Passed
TC-113 | Module 15 – Place Order | Verify Valid checkout | Order placed | Passed
TC-114 | Module 15 – Place Order | Verify Invalid name | Prevent submission | Passed
TC-115 | Module 15 – Place Order | Verify Invalid email | Prevent submission | Passed
TC-116 | Module 15 – Place Order | Verify Double click Place Order | Single order | Passed
TC-117 | Module 15 – Place Order | Verify Refresh confirmation | Expected behavior | Passed
TC-118 | Module 15 – Place Order | Verify Back button | Expected behavior | Passed
TC-119 | Module 16 – Order Confirmation | Verify Confirmation page opens | Success | Passed
TC-120 | Module 16 – Order Confirmation | Verify Customer name shown | Correct | Passed
TC-121 | Module 16 – Order Confirmation | Verify Purchased items listed | Correct | Passed
TC-122 | Module 16 – Order Confirmation | Verify Quantities shown | Correct | Passed
TC-123 | Module 16 – Order Confirmation | Verify Final total shown | Correct | Passed
TC-124 | Module 16 – Order Confirmation | Verify Gift message displayed | If provided | Passed
TC-125 | Module 17 – UI Testing | Verify Buttons aligned | Yes | Passed
TC-126 | Module 17 – UI Testing | Verify Inputs aligned | Yes | Passed
TC-127 | Module 17 – UI Testing | Verify Prices aligned | Yes | Passed
TC-128 | Module 17 – UI Testing | Verify Responsive layout | No overlap | Passed
TC-129 | Module 17 – UI Testing | Verify Font consistency | Consistent | Passed
TC-130 | Module 17 – UI Testing | Verify Button hover | Correct | Passed
TC-131 | Module 17 – UI Testing | Verify Disabled buttons | Styled correctly | Passed
TC-132 | Module 17 – UI Testing | Verify Error messages | Visible and readable | Passed
TC-133 | Module 18 – Boundary Testing | Verify Quantity = 1 | Works | Passed
TC-134 | Module 18 – Boundary Testing | Verify Quantity = inventory | Works | Passed
TC-135 | Module 18 – Boundary Testing | Verify Quantity = inventory+1 | Blocked | Passed
TC-136 | Module 18 – Boundary Testing | Verify Empty cart checkout | Prevented | Passed
TC-137 | Module 18 – Boundary Testing | Verify Max gift message | Handled | Passed
TC-138 | Module 18 – Boundary Testing | Verify Max name length | Accepted or validated | Passed
TC-139 | Module 18 – Boundary Testing | Verify Max email length | Accepted or validated | Passed
TC-140 | Module 19 – Negative Testing | Verify Browser refresh during checkout | No corruption | Passed
TC-141 | Module 19 – Negative Testing | Verify Multiple tabs | Cart consistency verified | Passed
TC-142 | Module 19 – Negative Testing | Verify Rapid clicking Add | Stable | Passed
TC-143 | Module 19 – Negative Testing | Verify Rapid clicking Checkout | Stable | Passed
TC-144 | Module 19 – Negative Testing | Verify JavaScript console errors | None | Passed
TC-145 | Module 19 – Negative Testing | Verify Invalid discount after valid | Correct behavior | Passed
TC-146 | Module 19 – Negative Testing | Verify Remove item during discount | Total recalculated | Passed
TC-147 | Module 19 – Negative Testing | Verify Empty all fields | Validation | Passed
TC-170 | Module 2 – Product Listing | Verify no broken images | Images load correctly | Passed
TC-171 | Module 2 – Product Listing | Verify price always has 2 decimal places | Currency formatted correctly | Passed
TC-172 | Module 2 – Product Listing | Verify product names are unique | No duplicate products | Passed
TC-173 | Module 2 – Product Listing | Verify Add to Cart button text | Button label is correct | Passed
TC-174 | Module 2 – Product Listing | Verify inventory label format | "In stock: X" displayed correctly | Passed
TC-175 | Module 2 – Product Listing | Verify page after browser zoom | Layout remains usable | Passed
TC-176 | Module 4 – Add to Cart | Verify Add product until stock exhausted | Last item can be added | Passed
TC-177 | Module 4 – Add to Cart | Verify Attempt another add after stock exhausted | Blocked | Passed
TC-178 | Module 4 – Add to Cart | Verify Add all products one by one | Cart updates correctly | Passed
TC-179 | Module 4 – Add to Cart | Verify Navigate away and return | Cart retained (if persistence expected) | Passed
TC-180 | Module 4 – Add to Cart | Verify Add item after removing same item | Works correctly | Passed
TC-181 | Module 6 – Cart Page | Verify cart row ordering | Matches order added (or defined order) | Passed
TC-182 | Module 6 – Cart Page | Verify price per item | Correct | Passed
TC-183 | Module 6 – Cart Page | Verify quantity displayed correctly | Accurate | Passed
TC-184 | Module 6 – Cart Page | Verify subtotal per line item | Correct | Passed
TC-185 | Module 6 – Cart Page | Verify currency symbol | "$" displayed consistently | Passed
TC-186 | Module 7 – Quantity Update | Verify Click minus when quantity=1 | Removes item or prevents decrement below 1 | Passed
TC-187 | Module 7 – Quantity Update | Verify Hold + button continuously | Inventory respected | Passed
TC-188 | Module 7 – Quantity Update | Verify Hold - button continuously | Quantity never negative | Passed
TC-189 | Module 7 – Quantity Update | Verify Alternate + and - rapidly | Correct quantity maintained | Passed
TC-190 | Module 7 – Quantity Update | Verify Quantity update recalculates tax immediately | Tax updated | Passed
TC-191 | Module 8 – Remove Item | Verify Remove first item | Remaining items intact | Passed
TC-192 | Module 8 – Remove Item | Verify Remove last item | Cart empty | Passed
TC-193 | Module 8 – Remove Item | Verify Remove all items individually | Empty cart displayed | Passed
TC-194 | Module 8 – Remove Item | Verify Remove after discount applied | Discount recalculated correctly | Passed
TC-195 | Module 8 – Remove Item | Verify Remove during checkout | Application behaves correctly | Passed
TC-196 | Module 9 – Discount Code | Verify Leading spaces before SAVE10 | Trimmed or rejected per requirement | Passed
TC-197 | Module 9 – Discount Code | Verify Trailing spaces | Same behavior | Passed
TC-198 | Module 9 – Discount Code | Verify SAVE10 twice | Discount applied once | Passed
TC-199 | Module 9 – Discount Code | Verify Invalid then valid | Valid works | Passed
TC-200 | Module 9 – Discount Code | Verify Valid then invalid | Previous discount handling verified | Passed
TC-201 | Module 9 – Discount Code | Verify Apply discount on empty cart | Prevented or handled | Passed
TC-202 | Module 9 – Discount Code | Verify Discount after quantity update | Recalculated | Passed
TC-203 | Module 9 – Discount Code | Verify Discount after remove | Recalculated | Passed
TC-204 | Module 10 – Price Calculation | Verify Subtotal becomes zero | Total reflects shipping rule | Passed
TC-205 | Module 10 – Price Calculation | Verify Large subtotal | Correct calculation | Passed
TC-206 | Module 10 – Price Calculation | Verify Decimal multiplication | Correct rounding | Passed
TC-207 | Module 10 – Price Calculation | Verify Tax rounded to 2 decimals | Currency formatting | Passed
TC-208 | Module 10 – Price Calculation | Verify Total rounded to 2 decimals | Currency formatting | Passed
TC-209 | Module 13 – Checkout Page | Verify Open checkout with empty cart | Blocked | Passed
TC-210 | Module 13 – Checkout Page | Verify Checkout after removing all items | Blocked | Passed
TC-211 | Module 13 – Checkout Page | Verify Checkout after discount | Total preserved | Passed
TC-212 | Module 13 – Checkout Page | Verify Checkout after browser refresh | Data retained or reset as specified | Passed
TC-213 | Module 13 – Checkout Page | Verify Back to cart from checkout | Cart preserved | Passed
TC-214 | Module 14 – Checkout Validation | Verify One character name | Validation | Passed
TC-215 | Module 14 – Checkout Validation | Verify Hyphenated name | Accepted | Passed
TC-216 | Module 14 – Checkout Validation | Verify Apostrophe in name | Accepted | Passed
TC-217 | Module 14 – Checkout Validation | Verify Unicode name | Accepted | Passed
TC-218 | Module 14 – Checkout Validation | Verify Numbers only | Validation | Passed
TC-219 | Module 14 – Checkout Validation | Verify Symbols only | Validation | Passed
TC-220 | Module 14 – Checkout Validation | Verify user@test.com | Accepted | Failed
TC-221 | Module 14 – Checkout Validation | Verify user.name@test.com | Accepted | Passed
TC-222 | Module 14 – Checkout Validation | Verify user+1@test.com | Accepted | Passed
TC-223 | Module 14 – Checkout Validation | Verify user@test | Invalid | Passed
TC-224 | Module 14 – Checkout Validation | Verify @test.com | Invalid | Passed
TC-225 | Module 14 – Checkout Validation | Verify user@.com | Invalid | Passed
TC-226 | Module 14 – Checkout Validation | Verify user@@test.com | Invalid | Passed
TC-227 | Module 14 – Checkout Validation | Verify user test@test.com | Invalid | Passed
TC-228 | Module 14 – Checkout Validation | Verify Unicode email | Validate per implementation | Passed
TC-229 | Module 14 – Checkout Validation | Verify 1 character gift message | Accepted | Passed
TC-230 | Module 14 – Checkout Validation | Verify Very long message | Handled | Passed
TC-231 | Module 14 – Checkout Validation | Verify Only spaces | Trimmed or accepted | Passed
TC-232 | Module 14 – Checkout Validation | Verify New lines | Preserved if supported | Passed
TC-235 | Module 15 – Place Order | Verify Press Enter to submit | Order placed if valid | Passed
TC-236 | Module 15 – Place Order | Verify Double-click Place Order | Single order created | Passed
TC-237 | Module 15 – Place Order | Verify Triple-click | Single order | Passed
TC-238 | Module 15 – Place Order | Verify Refresh immediately after submit | No duplicate orders | Passed
TC-239 | Module 16 – Order Confirmation | Verify thank-you message | Displayed | Passed
TC-240 | Module 16 – Order Confirmation | Verify order summary | Correct | Passed
TC-241 | Module 16 – Order Confirmation | Verify customer name | Correct | Passed
TC-242 | Module 16 – Order Confirmation | Verify quantities | Correct | Passed
TC-243 | Module 16 – Order Confirmation | Verify total | Correct | Passed
TC-244 | Module 16 – Order Confirmation | Verify gift message | Displayed if entered | Passed
TC-245 | Module 20 - Navigation | Verify Shop to Cart navigation | Navigation works | Passed
TC-246 | Module 20 - Navigation | Verify Cart to Shop navigation | Navigation works | Passed
TC-247 | Module 20 - Navigation | Verify Cart to Checkout navigation | Works | Passed
TC-248 | Module 20 - Navigation | Verify Checkout to Shop navigation | Works if allowed | Passed
TC-249 | Module 20 - Navigation | Verify Browser Back | Works correctly | Passed
TC-250 | Module 20 - Navigation | Verify Browser Forward | Works correctly | Passed
TC-251 | Module 21 - Persistence | Verify Refresh Shop page | Cart retained if specified | Passed
TC-252 | Module 21 - Persistence | Verify Refresh Cart page | Cart retained | Passed
TC-253 | Module 21 - Persistence | Verify Refresh Checkout | Form behavior verified | Passed
TC-254 | Module 21 - Persistence | Verify Open new tab | Cart persistence verified | Passed
TC-255 | Module 21 - Persistence | Verify Close and reopen browser | Persistence verified if supported | Passed
TC-256 | Module 17 – UI Testing | Verify Button disabled style | Correct | Passed
TC-257 | Module 17 – UI Testing | Verify Focus indicator | Visible | Passed
TC-258 | Module 17 – UI Testing | Verify Tab navigation | Logical order | Passed
TC-259 | Module 17 – UI Testing | Verify Error message color | Visible | Passed
TC-260 | Module 17 – UI Testing | Verify Input placeholders | Correct | Passed
TC-261 | Module 17 – UI Testing | Verify Alignment on small screen | Correct | Passed
TC-262 | Module 17 – UI Testing | Verify Alignment on large screen | Correct | Passed